## Live Ops Timeline
Live Ops - December
Start Date: | 2023-12-01
| fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun
Activities | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31
1. Offer the Dragon Bundle throughout the whole month, with a special discount on CE and NYE and option to buy it as a gift for another player | 2023-12-14: Winter Dragon Bundle; 2023-12-24: Christmas Eve; 2023-12-25: Christmas; 2023-12-26: Boxing Day; 2023-12-30: New Year's Eve; 2023-12-31: New Year
2. Customized Gacha box with Christmas surprises. | 2023-12-27: Christmas Gacha box
3. Customizable daily rewards, covering the period from Winter Solstice Event (and expected increase in DAU) to end of year. If possible, either make rewards progressively better for each consecutive day when the user logs in, or offer special daily rewards for every 7 days of consecutive log-ins. | 2023-12-25: Customizable daily rewards
4. Promotions on HC bundles, with a 40% discount. If possible, option to offer a bigger discount (50%) for first-time purchase of a HC bundle, and to users who have bought bundles in the past but have been inactive in the last 7 days. | 2023-12-14: Promotional HC bundles; 2023-12-26: Promotional HC bundles
5. Limited time event, with HC as the final prize, rewarding users in progressive milestones for spending Gold | 2023-12-20: Winter Solstice Event
6. Promotion on Gold SC, with different packs available at 50% reduced prices. | 2023-12-23: Gold Promotion
7. Limited time event, with an exclusive Dragon as the final prize, ranking users based on the total quantity of food spent feeding their dragons | 2023-12-29: Dragon feeding event
8. Promotion on Food SC, with different packs available at 50% reduced prices. | 2023-12-27: Dragon Food Promotion